MSS WALL BUILD

Implementation Plan & Execution Timeline

# Project Summary

Wall Dimensions: 19 ft (228") wide by 9.5 ft (114") tall

Aesthetic: High-end woodworking studio with warm wood tones, modern-industrial design

Scope: Complete wall covering + floating storage + workbench + display systems

# Phased Approach Overview

- Phase 1 (2-3 weeks): Procurement + Wall Prep

  - Order all materials; prep wall structure

  - Verify tools and safety equipment

- Phase 2 (3-4 weeks): Wall Installation

  - Install 24 sheets of Lauan plywood

  - Fill seams, sand, apply 2-coat oil finish

- Phase 3 (2-3 weeks): Support Infrastructure

  - Install blocking and mounting hardware

  - Build and install floating workbench (35 in) and shelf (53 in)

- Phase 4 (1-2 weeks): Storage & Organization

  - Install pegboard, lumber racks, bins, and lighting

  - Final organization and documentation

# Phase 1: Prep and Planning (2-3 weeks)

## Phase 1A: Material Procurement

Critical path: Order materials immediately to allow 5-10 day lead times

| Task | Lead Time | Responsible | Notes |
| --- | --- | --- | --- |
| Order Lauan plywood (24 sheets) | 3-7 days | You | Verify delivery to workshop |
| Order hardwood for shelf/bench | 5-10 days | Supplier | Kiln-dried, acclimated stock |
| Order shelf brackets (2) | 2-3 days | Amazon | $37.95 each |
| Order workbench brackets (2) | 2-3 days | Amazon | $23.25 each, heavy duty |
| Order wall control kits (2) | 5-7 days | Wall Control | $285/kit |
| Order storage bins (8 more) | 2-3 days | Lowes | Yellow lids, size check |

## Phase 1B: Wall Prep

Duration: 2-3 weeks (once materials arrive)

- Inspect wall for plumb, structural issues, and damage (2-3 hrs)

- Locate studs at 16 in centers; mark with pencil (2-3 hrs)

- Repair drywall imperfections; fill, sand, prime (4-6 hrs)

- Dry-fit first plywood sheet; verify seam plan and cuts (3-4 hrs)

## Phase 1C: Equipment Verification

- Confirm hand tools available: circular saw, level, stud finder, impact driver, nailer

- Procure consumables: wood filler, construction adhesive, sandpaper assortment

- Research wood oil options (boiled linseed, Danish oil); budget 40-60 dollars

# Phase 2: Wall Installation (3-4 weeks)

## Installation Process

- Sheet 1 (Test): 4-5 hours - dry-fit, nail pattern validation

- Sheets 2-12 (Left half): 4-5 days at 1-2 sheets/day

- Sheets 13-24 (Right half): 4-5 days; critical seam management

## Finishing Sequence

- Fill seams and nail holes with wood filler; let dry 24 hours (6-8 hrs work)

- Sand entire wall: 80-grit, then 120-grit (2-3 days)

- Final sand: 220-grit for smooth finish (1-2 days)

- Apply 1st oil coat; allow 48 hours cure (4-6 hrs application)

- Light 220-grit sand between coats (2-3 hrs)

- Apply 2nd oil coat; allow 72 hours cure (4-6 hrs application)

# Phase 3: Support Infrastructure (2-3 weeks)

## Phase 3A: Mount Points and Hardware

This phase can start in parallel with Phase 2 finishing

- Mark mounting locations at workbench (35 in) and shelf (53 in) heights (3-4 hrs)

- Install 2x4 blocking at strategic points for floating mounting (6-8 hrs)

- Install French cleats to distribute load across studs (4-5 hrs)

- Test load-bearing: verify 50 lbs/sq ft rating before proceeding (2-3 hrs)

## Phase 3B: Floating Workbench (35 inches from floor)

- Fabricate hardwood top: glue-up, flatten, final sand (4-6 days)

- Apply 2-coat oil to top; allow between-coat curing (3-4 hours active work)

- Fabricate bracket supports: mortise and tenon or heavy-duty bolts (3-4 hrs)

- Install brackets to wall studs using blocking points (4-5 hrs)

- Mount top to brackets; verify level and stability (2-3 hrs)

## Phase 3C: Floating Shelf (18 inches above workbench)

- Fabricate shelf: 16 ft length, 16 in depth, 1.5 in thick hardwood (3-4 days)

- Apply 2-coat oil finish; allow full cure time (3-4 hours active work)

- Install floating brackets (2): use wall control mounting hardware (3-4 hrs)

- Mount shelf on brackets; verify level within 1/8 inch (2-3 hrs)

- Add optional safety lip trim to shelf front (2-3 hrs)

# Phase 4: Storage and Organization (1-2 weeks)

## Phase 4A: Pegboard Installation

- Unbox wall control kits (2); verify all components (2-3 hrs)

- Design pegboard layout: sketch tool placement, mounting points (3-4 hrs)

- Install panel frames; secure to blocking, verify level (4-5 hrs)

- Mount pegboard accessories: hooks, baskets, tool holders (2-3 hrs)

- Hang hand tools; organize and label for accessibility (2-3 hrs)

## Phase 4B: Lumber Racks

- Assemble rack hardware: 3-arm sets, 2 separate configurations (3-4 hrs)

- Install racks above shelf; brace width calculated, evenly spaced (4-5 hrs)

- Verify load ratings; test with distributed weight (2-3 hrs)

- Stage hardwood boards by species and dimension (3-4 hrs)

## Phase 4C: Bin Staging and Lighting

- Organize and label storage bins (15 total with yellow lids) (2-3 hrs)

- Stage bins on shelf: evenly spaced, tight side-by-side layout (1-2 hrs)

- Install LED strip lighting under shelf; warm tone recommended (2-3 hrs)

- Final photography and documentation for completion (1-2 hrs)

# Critical Dependencies and Risks

## Critical Path

Phase 1 > Phase 2 > Phase 4 determines overall timeline. Phases 3A, 3B, 3C can overlap with Phase 2 after blocking is complete.

- Material procurement is critical (lead times 5-10 days)

- Wall installation must complete before pegboard installation

- Oil finish cure times enforce 48-72 hour gaps in schedule

- Hardwood acclimation: allow 2+ weeks before shelf/bench installation

## Key Risks and Mitigation

- Material delays: Order 2-3 weeks ahead; confirm delivery dates

- Wall not plumb: Use level throughout; shim plywood sheets; plan seams at studs

- Hardwood cupping: Acclimate 2+ weeks; monitor humidity; use kiln-dried stock

- Over-sanding veneer: Use progressive grits (80>120>150>220); light passes; block sanding

- Bracket failure: Load-test at 50 lbs/sq ft; double-mount; limit shelf load

- Oil finish not curing: Ensure ventilation; allow 72+ hours between coats

# Quality Checkpoints

- Dry-fit first sheet: Verify plumb, seam fit, no gaps before full install

- Wall plumb check: Less than 1/8 in deviation over 114 in height

- Seam quality: Flush, no ridges, smooth after sanding

- Surface prep: 220-grit smooth, dust-free before first oil

- Bracket load test: 50 lbs/sq ft distributed load holds safely

- Shelf level: Less than 1/8 in deviation, no flex under load

# Project Timeline Summary

Total Project Duration: 8-10 weeks (with parallel execution)

- Weeks 1-2: Phase 1 (Procurement and wall prep)

- Weeks 2-3: Begin Phase 1B while Phase 1A materials arrive

- Weeks 3-5: Phase 2A (Plywood installation)

- Weeks 4-6: Phase 3A in parallel (Blocking and mounts)

- Weeks 5-6: Phase 2B (Finish and oil)

- Weeks 5-7: Phase 3B and 3C (Workbench and shelf)

- Weeks 7-9: Phase 4 (Pegboard, racks, bins, and lighting)

- Week 9-10: Final documentation and photography